## table detail
▶Required Item
Issue# | Customer | PRODUCT TYPE | PRODUCT CODE | PROCESS | Function & Requirement | Fail Mode | Fail Effect | Fail Cause | Severity | Occurrence | Detection | A.P | Current Control | Recommended Action | Planed Date | Actual Date | Status | Responsible
PFMEA-NAN-#101 | ACTIA | TIA**(A) | 84060 | Feeding | Comply with RM input Q'ty (range ±2%) | Less/More RM Input | 1)Viscosity defect | 1.1)Abnormal Flowmeter tuning Sensor | 4 | 3 | 6 | L | 1.1.1)Annual calibration | Install Dual-Sensor with R6101's Loadcell | 11/11/25' | - | in Process | Zhang,Chen
[13 empty] | 1.1.2) Periodic sensor check | Replace faulty sensor | 11/11/25' |  | in Process | Zhang,Chen
[8 empty] | 1.2)Inaccurate RM ratio control | 4 | 4 | 6 | L | 1..2.1) Dosing system check | Improve ratio accuracy | 11/11/25' |  | in Process | Zhang,Chen
[13 empty] | 1.2.2) Operator verification | Provide operator training | 11/11/25' |  | in Process | Zhang,Chen
[7 empty] | 2)Hardness defect | 2.1) Low curing temperature | 4 | 2 | 6 | L | 2.1.1) Oven temperature monitoring | Adjust temperature setting | 11/11/25' | 11/8/25' | Completed | Zhang,Chen
[13 empty] | 2.1.2) Sensor calibration | Upgrade temperature control | 11/11/25' | 11/8/25' | Completed | Zhang,Chen
[8 empty] | 2.2) Short curing time | 3 | 4 | 5 | L | 2.2.1) Timer setting verification | Reset curing timer | 12/11/25' | - | Created | Zhang,Chen
[13 empty] | 2.2.2) Production log review | Revise process schedule | 11/11/25' | - | in Process | Zhang,Chen